## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 |  | Introduction to Project,AI,ML and Langchain | MUST HAVE | No Dependency | Divya prakash | 3- Completed
S2 | S2 |  | Implementation of langchain, langchain memory | MUST HAVE | Gemini API | Divya prakash | 3- Completed
S3 | S3 |  | Indexing & Retrieval | MUST HAVE | Pinecone | Divya prakash | 3- Completed
S4 | S4 |  | Speech to speech recognition | MUST HAVE | No Dependency | Divya prakash | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to Project | 2025-02-24 | 2025-02-25 | Divya prakash | Others | 3- Completed
US-002 | TID-02 | Implementation of langchain, langchain memory | 2025-03-01 | 2025-03-05 | Divya prakash | Coding | 3- Completed
US-003 | TID-03 | Indexing & Retrieval | 2025-03-10 | 2025-03-14 | Divya prakash | Coding | 3- Completed
US-004 | TID-04 | Speech to Speech recognition | 2025-03-15 | 2025-03-28 | Divya prakash | Coding | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentor and team
Sprint 2 | Day 8 | Got errors while implementing the bot | Cleared after attending class and asking with team mates
Sprint 3 | Day 17 | Found difficult in Pinecode environment set up | Solved it by asking to the mentor
Sprint 4 | Day 24 | Got lot of error in last step in the project | Cleared my doubts and error from the class session

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 24/2/2025 | 28/2/2025 | Divya prakash | Basic Langchain Project | Issue with credentials | Created Google Cloud Account | installed credentials and included in my code
2 | 2 | 2025-01-03 | 2025-07-03 | Divya prakash | langchain memory | issues in implementation | Implemented memory | debugged the error occurred in the code
3 | 3 | 2025-10-03 | 14/3/2025 | Divya prakash | Indexing & Retrieval | got errors in retrival part | done doc index & retrival | cleared errors in reteival part & pinecone
4 | 4 | 14/3/2025 | 28/3/2025 | Divya prakash | Speech Recognition | difficult in the last step | Finished Speech recognition | debugged the error using subprocess
5
6
7